## Sheet1
Sno | Client | Project | Task Type | Module/Form Name | Requirement/ Change/Defect Description | Reference | Estimated Time (hrs) to close | Assigned to | Priority | Status | Remarks / Comments
1 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Head Office Module | Development of No of User Logins to access the MIS Report | work order |  | Srikanth | High | Completed
2 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Enquiry Module | Development of entry form for enquires | work order |  |  | High | Completed
3 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Mobilization Module | Need to develop dashboard for call centres as like Sangareddy Health Call centre for following up enquires | work order |  |  | High | Completed
4 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Mobilization Module | Provision to update Mobilzed candidate details status | work order |  |  | High | Completed
5 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Training Center Module | Course wise Fees Masters | work order |  |  | High | Completed
6 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Accounts Module | Provision to update the fee details (Installments / Full) | work order |  | Srikanth | High | Completed
7 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Accounts Module | Generation of Receipts | work order |  | Srikanth | High | Completed
8 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Accounts Module | Dashboard for following up pending payments from students | work order |  | Srikanth | High | Completed
9 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | HR Placement Module | Provision to capture trainees details sent to employers and status of the employee interview for retail courses only | work order |  | Srikanth | High | Completed
10 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Head Office Module | Placement % Report for batch wise, TC wise and employer wise | work order |  | Srikanth | High | Completed
11 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Individual logins to students | work order |  |  | High | Cancelled
12 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Provision to update Question papers and answer sheets | work order |  |  | High | Cancelled
13 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Verification of Answers and genertaion of results | work order |  |  | High | Cancelled
14 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Provision to update the student results | work order |  |  | High | Cancelled
15 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Provision to conduct online, offline & Mock interviews | work order |  |  | High | Cancelled
16 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Online Exmanination Module | Provisino to conduct extenal assessment | work order |  |  | High | Cancelled
17 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | SMS & Email Integration | In every module at every state SMS and email should be sent to concern persons | work order |  | Srikanth | High | Completed
18 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Feedback Form | Need to develop Feedback form for Faculty on Student in retail project | work order |  |  | High | Cancelled
19 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Feedback Form | Need to develop Feedback form for Student on Faculty in retail project | work order |  |  | High | Cancelled
20 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Accounts Module | Need to give provision to update Training centre expenditure and need to show P& L statement | work order |  | Srikanth | High | Completed
21 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Reports | Report on Expenses vs Revenues | work order |  | Srikanth | High | Completed
22 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Reports | Report on No of students Vs Placement | work order |  | Srikanth | High | Completed
23 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Reports | Reprot on Target Vs Achieved | work order |  | Srikanth | High | Completed
24 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Training Center Module | One student can register under multiple courses | work order |  | Srikanth | High | Completed
25 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Training Center Module | Duplicate Registrations need to identified | work order |  | Srikanth | High | Completed
26 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Reports | Capture and display information and trigged alarm about following activities performed or not for each batch Mock interviews Quiz Site Visit Engineers to go Technician Lab CAD Lab Expert Talk | work order |  | Srikanth | High | Completed
27 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Trainer module | Need to give provision to update the Curriculum schedules for the training with admin followup | work order |  | Srikanth | High | Completed
28 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | MIS | Need to change the Orion MIS for Dhanush |  |  |  | High | Completed
29 | Dhanush Engg Services Pvt Ltd | Skills MIS | MIS | Prototype link | Need to give demo on Prototype and deadline for this project to deliver same by October end |  |  | Sunitha | High | Completed
30 | Dhanush Engg Services Pvt Ltd | Skills MIS | MIS | Enquiry Module | Import optoin for uploading enquiries in BDM login | Additional Requirements |  |  | High | Completed
31 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Need to provide one more coloumn no of Enrollments in dashboard | work order |  | Srikanth | High | Completed
32 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Need to fix the feedback given by Dhanush team through spread sheet on head office module | Bug Fixing |  | Srikanth | High | Completed
33 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Enquiry Module | Enrollment number generation as per the format given Registration number format should be 12 digits. First 2 digits will be shortcut for source of enquiry + 4 digits of year + 2 digits of month + 4 digits of running serial number. Eg: MI2017090001 | work order |  | Srikanth | High | Completed
34 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Training Centre Registration | Need to devlop Project registration, Project allocation & project status closing | work order |  | Srikanth | High | Completed
35 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Training Centre Registration | Need to remove the unused forms from this module and set right the menu as per our requiments document |  |  | Srikanth | High | Completed
36 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Training Centre Registration | Need to Customize the existing forms like OJT, Attendance, Off line examination, Expenditure entry etc |  |  | Srikanth | High | Completed
37 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Head office | In Training centre registration need to add the password enable option when page is refreshing, which is resolved in add staff form | Bug Fixing |  | Srikanth | High | Completed
38 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Head office | Need to address the Head office module feedback given to us | Bug Fixing |  | Srikanth | High | Completed
39 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Need to address the enquiry module feedback give to us | Bug Fixing |  | Srikanth | High | Completed
40 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Need to remove mandatory options in Enquiry registration form except Name, Mobile No, Email & Source of enquiry | work order |  | Srikanth | High | Completed
41 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Need to add one more column in enquiry form under mobile number that is type of Courses looking for dropdown (Government / Retail / Both), depending on the above courses need to populated | Change Request |  | Srikanth | High | Completed
42 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | Whole application design need to be modified to change the look and feel of the application |  |  | Srikanth | High | Open
43 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry Module | In Enquiry dasboard under dashboard grid need to provide search with update option there itself | Change Request |  | Srikanth | High | Completed
44 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | Need to give them time lines to complete the changes |  |  | Srikanth | High | Completed
45 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Add trainee | Need to provide them Add trainee form excel for porting | Work Order |  | Srikanth | High | Completed
46 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enqyiry dashboard | Need to work on the Revisd BD and FO flow as per their mail dated 17.01.2018 | Work Order |  | Srikanth | High | Completed
47 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Placement details | Self Employment need to be incorporated in placement - which need to be discussed | Additional Requirements |  | Srikanth | High | Completed
48 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Placement details | Need to add Project Type in Project Registrations | Work Order |  | Srikanth | High | Completed
49 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Attachments | Need to change the attachments to folder saving | Work Order |  | Srikanth | High | Completed
50 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Login | Need to work on the role based menu sent by dhanush team on Jan 22nd | Work order |  | Srikanth | High | Completed
51 | Dhanush Engg Services Pvt Ltd | Skills MIS | Deletion | MIS | Need to delete the test records as per their whats app message | Bug Fixing |  | Srikanth | High | Completed
52 | Dhanush Engg Services Pvt Ltd | Skills MIS | MIS | MIS | Need to send the status report to Dhanush with pending tasks with their status |  |  | Sunitha | High | Open
53 | Dhanush Engg Services Pvt Ltd | Skills MIS | Reports | Reports | Need to develop the reports if any as per their requirement. | Work order |  | Srikanth | High | Open
54 | Dhanush Engg Services Pvt Ltd | Skills MIS | Testing | MIS | Need to test the application througly to make error free 1. Revised BD Flow 2. Import option testing with their given excel data | Bug Fixing |  | Dhanlaxmi | High | Completed
55 | Dhanush Engg Services Pvt Ltd | Skills MIS | Master Page | MIS | Need to give master page for displaying the IDs for import option for trainee registration form | Work order |  | Manikanta | High | Completed
56 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Role Matrix | Need to work on dynamic Role matrix depending on the Login for Access, View & Edit | Additional Requirements |  | Outsource | High | Open
57 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | when we change the status of enquiry to dropout, we don't have a option to get back to followup or walk in or registered, status changing option is needed in Dropout. | Bug Fixing |  | Abhilash | High | Completed
58 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | if we change the status of enquiry to followup of next week date, it is visible in due for walk in, it should not visible in due for walk in. | Bug Fixing |  | Abhilash | High | Completed
59 | Dhanush Engg Services Pvt Ltd | Skills MIS | New Requirement | Report | Needed date wise report of BDE in their logins, if we select date then the activity of BDE should be displayed with date, name, contact no.,status,source of enquiry and remarks . If possible search box needed to find the enquiry by searching with their names.(the same option also needed in BDM login to check activity of all BDE's.) | Additional Requirements |  | Abhilash | High | Completed
60 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | In drop down of changing status, if the candidate interested in walk in what option needed to select ? please insert "due for walk in" in drop down all those can be displayed in "Due for walk in" column. | Change request |  | Abhilash | High | Completed
61 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | needed to add column between "due for follow up today" and "due for walk in" with all the enquires displayed here (latest updated enquiry displayed at top) & | Bug Fixing |  | Abhilash | High | Completed
62 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Import option | Need to change the Static Id columns like (Gender, Qualification etc) in add trainee import option |  |  | Abhilash | High | Completed
63 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | MIS | Need to give text boxes for search in all the drildowns of the enquiries | Additional Requirements |  | Abhilash | High | Completed
64 | Dhanush Engg Services Pvt Ltd | Skills MIS | Change Request | Enquiry dashboard | Need to work on latest revised BDE and FO dashboard flow as per Monday skype call and mail dated 12.02.18 | Change Request |  | Abhilash | High | Completed